## DWAR
Rig Name Here
Daily Work Activity & STOP Report
Report Date |  | 2009-07-02 |  |  | Days on Location |  |  |  | 58
Location |  | abcde |  |  | Operator
O.I.M. |  | J Bloggs |  |  | Supervisor |  |  |  | xxxxx
Work Summary
Drilling | # | % Comp | Task
| 1 | 40 | Carry out Planned maintenance
| 2 | 90 | Assist FMC with work On EDP / LRP
| 3 | 50 | Paint Pump Room / Pit room areas
|  | 69 | % as per CAS compliance spreadsheet at the start of the month from ABZ
|  | 16 | CAS Assessments completed this month
| 3rd Party Man Hours |  |  |  | Monthly Cumulative Hours
Electrical | # | % Comp | Task
| 1 | 25 | Planned maintenance
| 2 | 100 | Competence assurance, fse e-learning
% as per CAS compliance spreadsheet at the start of the month from ABZ
|  | 3 | CAS Assessments completed this month
| 3rd Party Man Hours |  |  |  | Monthly Cumulative Hours |  |  |  | 72
Engineering | # | % Comp | Task
| 1 | 90 | Roughneck shelterheater, in operation, still some insulation to do
| 2 | 55 | Weekly routines
| 3 | 100 | Functioned quick closing valve 701-101A, moves smooth again
| 4 | 90 | Platform for ct winch powerpack/control
| 5 | 35 | Introducing Mechanic to routines. Competence assurance
|  | 77 | % as per CAS compliance spreadsheet at the start of the month from ABZ
|  | 20 | CAS Assessments completed this month
| 3rd Party Man Hours |  |  |  | Monthly Cumulative Hours
Marine | # | % Comp | Task
|  | 100 | Helicopter
|  | 100 | Lifted EDP up to LRP stack
|  | 100 | Working storemans list
|  | 85 | Weekly PMs
|  | 100 | Seafastening on deck
|  | 88 | Housekeeping ongoing
|  | 90 | Cleaning ongoing
|  | 100 | Worked Skandi Stolmen
|  | 100 | Worked Island Challenger
|  | 40 | Prepared Backload for next boat
|  | 87 | % as per CAS compliance spreadsheet at the start of the month from ABZ
|  | 10 | CAS Assessments completed this month
| 3rd Party Man Hours |  |  |  | Monthly Cumulative Hours
OIM/Safety | # | % Comp | Task
| 1 | 100 | CAS
| 2 | 100 | Onboard training
| 3 | 100 | Clean up RSWM index
| 4 | 100 | Daily walkabout
| 5 | 100 | Area inspection
|  | 99 | % as per CAS compliance spreadsheet at the start of the month from ABZ
|  | 1 | CAS Assessments completed this month
| 3rd Party Man Hours |  |  |  | Monthly Cumulative Hours
Subsea | # | % Comp | Task
| 1 | 100 | Grease MRT's on line and #3 GLT
| 2 | 100 | Rebuild and test 1/2 regulator ex diverter panel
| 3 | 100 | Investigate problems with #4 riser torque tool
|  | 42 | % as per CAS compliance spreadsheet at the start of the month from ABZ
|  | 4 | CAS Assessments completed this month
| 3rd Party Man Hours |  |  |  | Monthly Cumulative Hours
Audits
Audit By | Date Due | % Comp | Required Actions
DNV for ISPS ,ISM | 30 Jun 2009 | 100% | 4 NCR raised , 2 closed 2 open
DPR | 24 Jul 2008 | 95 | Electrical audit. 1 open item.
STOP CARDS - 02 Jul 2009
| Totals |  | Positive |  | Corrective (24 hour) |  |  | Corrective (Monthly To Date)
| 24Hr | MTD | 24Hr | MTD | High | Med | Low | High | Med | Low
3rd Party | 3 | 111 | 3 | 70 | 0 | 0 | 0 | 0 | 0 | 41
Catering | 1 | 13 | 0 | 7 | 0 | 0 | 1 | 0 | 0 | 6
Drilling | 8 | 212 | 8 | 193 | 0 | 0 | 0 | 0 | 0 | 19
Electrical | 1 | 162 | 1 | 134 | 0 | 0 | 0 | 0 | 0 | 28
Engineering | 1 | 77 | 1 | 63 | 0 | 0 | 0 | 0 | 0 | 14
Marine | 4 | 141 | 3 | 111 | 0 | 0 | 1 | 0 | 0 | 30
OIM/Safety | 5 | 89 | 3 | 61 | 0 | 0 | 2 | 0 | 1 | 27
Operator | 0 | 9 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 7
Subsea | 0 | 12 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 1
Total | 23 | 826 | 19 | 652 | 0 | 0 | 4 | 0 | 1 | 173
| Total Year to Date |  | Positive Cards Year to Date |  | Corrective Cards Year to Date
[5 empty] | High |  | Medium |  | Low
Total | 7052 |  | 4951 |  | 0 |  | 9 |  | 2091